## Лист1
WBS Number | Task description | Estimates
1 | Client/Server application to get mouse activity on remote HOST | 38 h
1.1 | Create a server side using Windows Sockets | 7.5 h
1.1.1 | Creating a socket for the server side | 1 h
1.1.2 | Bind the created socket to an IP address and port | 0.5 h
1.1.3 | Create a log file | 0.5 h
1.1.4 | Listen on a socket for incoming connection requests | 1 h
1.1.5 | Accept connection requests on created listening socket | 0.5 h
1.1.6 | Receive data from socket | 1 h
1.1.7 | Write the received data to log file | 1 h
1.1.8 | Shut down the client socket | 0.5 h
1.1.9 | Close socket | 0.5 h
1.1.10 | Exit | 0.5 h
1.1.11 | Close the log file | 0.5 h
1.2 | Create a client side using Windows Sockets | 5.5h
1.2.1 | Creating a socket for the client side | 1 h
1.2.2 | Connect to the server socket | 0.5 h
1.2.3 | Get mouse coordinate each 500ms | 0.5 h
1.2.4 | Store mouse coordinate | 0.5 h
1.2.5 | If right button clicked, get and store coordinates | 0.5 h
1.2.6 | If left button clicked, get and store coordinates | 0.5 h
1.2.7 | Send data to server side | 1 h
1.2.8 | Close the socket | 0.5 h
1.2.9 | Exit | 0.5 h
1.3 | Make application cross-compile | 15 h
1.4 | Create makefile to compile application | 10 h